## QA Bug Report
QA Test Report – Tichi Web Application
Application | Tichi Web Application (Stage)
Tester | Harish S
Date | 01-07-2026
Bug ID | Title | Priority | Severity | Expected Result | Actual Result | Screenshot
BUG-001 | User gets stuck after leaving OTP verification | High | High | Resume/Resend verification | User Already Exists + Email not verified | User Already Exists, Email not verified
BUG-002 | OTP countdown remains at 15 | Medium | Medium | 15→0 countdown | Stays at 15 | OTP screen
BUG-003 | Refresh on OTP page returns to Signup | Medium | Medium | Stay on OTP page | Redirects to Signup | Refresh screen
BUG-004 | Internal server error during concurrent login (Needs confirmation) | High | High | Graceful handling | Internal server error | Internal server error
UX-001 | No recovery after Email not verified | Medium | Medium | Provide Verify/Resend option | No recovery option | Login screen
Passed Test Cases
Forgot Password flow | PASS
Password reset | PASS
Old reset link invalid after use | PASS
Browser autofill | PASS